## Monthly Product Release Gantt
MONTHLY PRODUCT RELEASE GANTT CHART
[8 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
ID | PORTFOLIO | STATUS | OWNER | DEPENDENCIES | START DATE | END DATE | DURATION | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
1 | PRODUCT ID |  |  |  | 2025-01-20 | 2025-09-27 | 180
1A | Release 1 | Complete |  |  | 2025-01-20 | 2025-04-12 | 60
1B | Release 2 | In Progress |  |  | 2025-02-25 | 2025-06-30 | 90
1C | Release 3 | On Hold |  |  | 2025-05-15 | 2025-08-11 | 63
1D | Release 4 | Needs Review |  |  | 2025-06-15 | 2025-09-27 | 75
2 | PRODUCT ID |  |  |  | 2025-02-25 | 2025-11-05 | 182
2A | Release 1 | Overdue |  | 1A | 2025-02-25 | 2025-05-20 | 61
2B | Release 2 | Not Started |  |  | 2025-04-01 | 2025-08-03 | 89
2C | Release 3 | Not Started |  |  | 2025-06-25 | 2025-09-20 | 63
2D | Release 4 | Not Started |  |  | 2025-07-21 | 2025-11-05 | 78
3 | PRODUCT ID |  |  |  | 2025-04-12 | 2025-11-30 | 165
3A | Release 1 |  |  | 1D | 2025-04-12 | 2025-07-13 | 65
3B | Release 2 |  |  |  | 2025-05-23 | 2025-09-27 | 91
3C | Release 3 |  |  |  | 2025-08-15 | 2025-11-12 | 64
3D | Release 4 |  |  |  | 2025-09-08 | 2025-11-30 | 60
4 | PRODUCT ID |  |  |  | 2025-06-01 | 2025-12-22 | 146
4A | Release 1 |  |  | 1A, 2A | 2025-06-01 | 2025-07-29 | 42
4B | Release 2 |  |  |  | 2025-07-08 | 2025-11-14 | 94
4C | Release 3 |  |  |  | 2025-09-20 | 2025-11-14 | 40
4D | Release 4 |  |  |  | 2025-09-22 | 2025-12-22 | 66
Formulas:
DURATION = NETWORKDAYS([START DATE],[END DATE])