## Sheet1
Project Name | Event ABC
Project Manager | Anthony G.
Action | Responsible | Priority | Status | Start Date | End Date | Notes
Goal #1: Select Venue
Identify venue options | Sally J. | High | Complete | 2015-09-30 | 2015-10-02
Visit venues | Sally J. | High | Complete | 2015-10-05 | 2015-10-09 | Must send contracts by 10/10
Sign contract | Maria S. | High | Complete | 2015-10-12 | 2015-10-12
Goal #2: Secure Speakers
Recruit speakers | Sally J. | High | In progress | 2015-10-07 | 2015-10-12
Speaker bios | Sally J. | Medium | Not started | 2015-10-12 | 2015-10-14
Create and send speaker packets | Maria S. | Medium | Not started | 2015-10-13 | 2015-10-16 | Send to stakeholders
Confirm speakers | Sally J. | High | Not started | 2015-10-17 | 2015-10-18
Goal #3: Recruit Sponsors
Identify sponsors | John S. | High | In progress | 1902-10-13 | 2015-10-19
Write up sponsor agreement | Maria S. | Medium | Not started | 2015-10-15 | 2015-10-16
Send emails | John S. | High | In progress | 2015-10-19 | 2015-10-21
Make cold calls | John S. | Medium | Not started | 2015-10-21 | 2015-10-23 | From sales team
Goal #4: Promote event
Create banners | Morgan K. | Low | Not started | 2015-10-26 | 2015-10-28
Order swag | Morgan K. | Low | Not started | 2015-10-28 | 2015-10-28 | Coffee mugs, totes, pencils
Create social media strategy | Corrine J. | Low | In progress | 2015-10-13 | 2015-10-26
Make marketing materials | Karen Z. | High | Not started | 2015-10-26 | 2015-10-30