## Master Task List
SAMPLE TRANSITION PLAN
Task Name
Corporate
Jones Lang LaSalle approval of Proposal
Finalized Contract between JLL and Corporate
Secure and deliver all contractually obligated insurance certificates to Jones Lang LaSalle
Prepare a Contract Summary Guide for all management and supervision
Review PSA: Create categorical Summaries
Operational Requirements
Definitions
Pricing
Reports
Start up Deadlines
Equipment purchases
Supply (Chemicals & Paper) purchases
Procedures
Billing requirements
Locations with street addresses and customer designations
Customer conatct info by location
Assemble existing SOPs
Review all collected SOPs for PSA compliance
Develop new SOP's requried to comply with PSA
Start-Up Team selection and assembly for preliminary review of entire Transition Plan. Present final Transition Plan to Jones Lang LaSalle for review and acceptance
Senior Management to meet with Jones Lang LaSalle management to review the contractual scope of work and ensure compliance with same
Senior Management to attend Jones Lang LaSalle meetings, as required
Senior Management and Account Manager to meet with dedicated supervisors and line staff to report on initial staff performance
Senior management to meet with Triangle dedicated management to review the contractual scope of work and ensure compliance with same
Management to review all policies and protocols to ensure complete compliance with same
Management to meet with MWBE representative to review all policies and protocols to ensure compliance with corporate and Jones Lang LaSalle policies
Define and review monthly reporting formats with management
Define weekly reporting needs and format with management
Distribute summaries to start up team members, operations and Corporate
Establish audit process for measuring PSA compliance w/ corrective action
Plan audit dates
Assign responsibility for audits
Develop & Document Quality Plan-including inspection process
Develop & Document inspection forms (Local & Corporate and Customer)
Develop Customer Satisfaction Surveys
Review & Get Customer Approval on CS Surveys
Document Customer Satisfaction Process & Surveys (frequency, measurement, & feedback)
Document Compliment/Complaint Process
response, tracking, investigation, corrective action, Customer satisfaction resolution
Review management rules of authority
Review all (accounting, operations, safety, IT, etc) processes with local management (turnover)
Financial /Accounting
Obtain /review costing
Develop budget
Notify Corporate
Confirm codes, unit pricing etc
Set up in JDE
Confirm Local Tax Requirements
Coordinate/confirm with Corporate
License Company To Do Business In State
Sales Tax Certificate
State Tax Registration
Workers Compensation Policy Coverage & Reporting Forms
Liability Insurance Coverage & Reporting Forms
Unemployment Insurance Certificate
Certificate of Insurance for Customer
Performance Bond
Bank Accounts
Credit For Vendors
Check Cashing Arrangements
Establish communication between Corporate Staff and appropriate customer staff
Establish a Jones Lang LaSalle account employee time clock payroll system
Establish internal financial reporting controls and account codes
Develop and Document key accounting processes
Accounts payable (includes requisition procedure)
Billing (includes how customer would like to see invoice)
Payroll - determine how to process
Human Resources
Review/Confirm staffing requirement and authorized position pay rates
Prepare/review Position Descriptions
Prepare recruiting plan
Place advertisements for required positions
Coordinate with Corporate notifying all BU's of open positions
Define candidate screening criteria (best candidate)
Document screening criteria for future replacement
Begin screening candidates
Prepare new hire packets
Schedule interviews
Review all interviewed candidates for consideration
Commence background checks and employment documentation of any Jones Lang LaSalle proposed candidates that have been offered and accepted positions
Make final staffing recommendations
Select & Hire (final) qualified staff with Operations
Outline compensation, benefits and job description with selected candidates
Offer positions and obtain signed Letter of Understanding for each position
Obtain signed restrictive covenant from Management hires
Identify orientation and training requirements
Gov't mandated, company values, equipment & chemical training
Prepare orientation and training materials
Prepare orientation and training schedule
Set up targeted job tax credits (WOTC) if applicable
Set up Employee personnel files
Designate shift assignments of all positions
Develop Organization chart with position names, phone numbers, & other pertinent info
Incorporate Organization Chart into Master Organization chart
Forward all documentation requirements to Corporate
Ensure all training is completed per requirements
contact list of company expertise (including outside support)
Prepare & Document disaster recovery system
Prepare & Document absenteeism replacement or service interruption process
Prepare & Document employee retention program
Awards, commendation letters, core values, publicly acknowledge, communications length of service, attendance, safety, other KPI performance
Prepare & Document employee Performance Appraisal system
Post Federal and State labor law poster(s)
CMMS or Manual
Review Cleaning Schedules for Tasking
Identify Tasking and Frequencies for Staffing
Define Tasking and Estimated Times for Scheduling of Staff
Verify Accuracy and Completeness of Tasking
Set up reports required per contract requirements
Determine/request input from customer re: their reporting requirements
Document Quality plan
Determine how work requests will be received from customer (phone, email, direct access call center, ect.)
Equipment & Supplies
Complete inventory of Airport Purchased Equipment and place order if needed for new equipment
Disposables initial order processed
Take delivery of all supplies and conduct inventory check
Field test all equipment
Validate supply inventory levels
Safety
Identify Safety officer forwarding contact information to the Director of Safety
Complete Certification of Hazard Analysis. Signed copy retained in the site safety records. Copy forwarded to the Director of Safety.
Identify Personal Protective Equipment cited on the Certification of Hazard Analysis
Conduct and document training for use and care of personal protective equipment for each employee
Set up Occupational Injury, Auto Loss and General Liability reports
Require all personnel to sign off acknowledging accident reporting procedure with copies sent to Director of Safety
Print Corporate Safety Manual printed and make available to all employees
Complete/document training session for all employees concerning contents and location of Corporate Safety manual
Develop site specific safety handbook
Conduct/document training conducted for site specific safety manual awareness
Confirm Job Hazard Analysis procedure and form are on site
Complete New Hire Orientation form for each employee
Employee training document template on site
Set up Monthly Safety Training attendance record template
Set up Annual Safety Training Topic template
Create MSDS book in accordance with corporate policy
Training for MSDS and chemical use has been completed and documented for all employees
Chemical storage area(s) organized in accordance with corporate policy
Confirm flammable storage lockers on site for storage of ALL flammable materials
Secure training areas
Conduct classroom training of janitorial staff
Identify occupational health facility, which will provide new hire physicals, drug and alcohol screening and work related injury care.
Verify first aid kit is on site and sufficient for number of employees in the work center, install if needed.
Post any safety poster(s)
Verify that offices and work areas have proper signage, install if needed (first aid kit, eye wash station, fire extinguisher, hearing protection areas, stretcher, etc)
Refresher safety and security orientation and training with staff and MWBE staff
Security and safety orientation of Jones Lang LaSalle protocols
Modify training materials according to Jones Lang LaSalle standards
Determine safety and security policies and regulations in accordance with Jones Lang LaSalle security policies and procedures
Administrative
Identify/secure office space
Identify/secure locker room space
Identify/secure storage space
Identify/secure office furniture and basic office set up supply requirement
Identify/secure communication requiremnts w/ IT department
Computer, fax, electronic time keeping, Phone lines or cable, cell phones
Secure company and JLL ID Badges for all employees
Requisition/purchase authorized office equipment
Order corporate signage for door, if required
Order business cards for authorized personnel
Order stationary, company forms, and stationary supplies
Identify required keys and or lock codes for space
Coordinate start up with VP of HR, Director of Safety, CFO, and COO to confirm that all items needed for account setup and required documentation have been received.
Submit Material Safety Data Sheets (MSDS) on planned chemicals to Jones Lang LaSalle for review and approval, as required
Define any customer service, procedural and QC forms required by Jones Lang LaSalle
Create above forms, as required, and review for accuracy with Jones Lang LaSalle
Transition and start-up meetings with local Jones Lang LaSalle management
Conduct introductory meetings with Jones Lang LaSalle local operations department heads
Core Values - posted in office
Operations
Obtain Purchase Order or copy of signed Contract
Review contract requirements
Evaluate Start-Up Team Requirements
Select Start-Up Team Individuals
Assign Category Coordinators
Select Start-Up Team Leaders
Define Start-Up Team Lines of Authority & Responsibility
Define and communicate expense guidelines to start up team
Set Up Pre-Planning Meeting with Start-Up Team
Prepare list of key requirements for distribution to all start up staff
Set Up staffing plan including start/stop times
Set up emergency contact procedures including how to contact all staff
Establish planned lines of communications with Customer
Requisition, purchase, obtain required materials and equipment
Capital equipment
Supplies
Uniforms
Conduct uniform fittings
Order uniforms
Distribute uniforms
decide how to wash mop heads and rags
Forward Insurance Certificate to Customer
WorkLoad Facilty to determine:
Manhours, cleaning tasks & asignments, equipment requirements
Document work loading assignments w/ time allocation, proper chemicals & equipment)
Develop & Document process to handle out of scope work
(special requests with time of completion, emergency, disaster)
Finalize Job Costing Budget (Cost Analysis Sheet)
Set up Budget Control Process (labor hours & $, supplies) w/ corrective action if over budget
Get Approved vendor list of suppliers/equipment manufacturers and subs
Finalize/sign Agreement with Subcontractors - provide insurance, non compete, agrees to follow all procedures at site
Get W9 Forms from Subcontractors
Get Insurance Certificates from Subcontractors
Meet with JLL Security representative to review security requirements, including the following:
Sign In Requirements
Alarm Systems
Key or Access Card Systems
Safety and Emergency Procedures
Trash Handling Requirements
Areas to be Cleaned with Tenant or Security Present
Call in 3 approved equipment manufactures to recommend best equipment usage
Have each equipment manufacturer provide benefits over competitor equipment
Get equipment spec, warranties, training requirements, equipment maintenance requirements
Call in 3 approved distributors to recommend best chemical usage
Have each distributor provide benefits over competitor chemicals
Get chemical spec, warranties, training requirements, MSDS sheets on all cemicals
Develop and document an approved vendor, equipment, & chemical plan
Develop and document an inventory control plan
Develop and implement an equipment maintenance PM program to match manufacturer's spec
Conduct any skill training required (equipment & chemical)
Information Technology
Hardware requirements
Identify office equipment requirements inclduing telephone, fax
machine, internet, copier, computer's, answering machine, etc
Submit hardware required to IT Dept
Hardware ordered from vendors and shipped to support company for configuration
Hardware shipped to new site
Software requirements
Confirm standard office package (utilities, Adobe Reader, Office)
Identify additional software or needs (JDE, EAM )
Phone requirements
Order necessary lines and equipment for new site
Data requirements
Order necessary lines and equipment for new site
Firewall hardware shipped to support company for configuration
Office network wiring installed and additional hardware ordered
Network tested and documented
Mobile phone requirements
Preferred vendor is selected
Hardware types are decided
Hardware shipped to new office
Secure all Jones Lang LaSalle e-mail addresses and telephone contacts, distribute to appropriate internal staff
Review and conform to company polices
Note on A226: John Ruppel: Triangle IT needs to know how many computers, monitors, printers etc the office requires. Once Triangle IT has a complete list, the equipment will be ordered and shipped to Triangle IT Support Group for configuration. It will then be shipped to the designated address. Setup and configuration will be coordinated by Triangle IT Support Group along with site liaison or site management. All future purchases will be coordinated with IT as well.
Note on A232: John Ruppel: All Triangle computers have the XP operating system installed as a standard. They are also pre configured with MS Office 2003 and Adobe Acrobat Reader. If the office or site requires any additional software, these will be purchased and installed by Triangle IT as part of the hardware setup.
Note on A235: John Ruppel: Our preferred phone vendor is Verizon. Either Triangle IT or the liaison/site management can initiate the order request for telephone service at least 6 weeks prior to site startup date. The billing contact must be submitted as Triangle Corporate location along with 3 authorized contacts on the account. These contacts are (1) Accounts Payable staff members (2) Triangle Administration staff members and (3) Triangle Information Technology staff members. After the second bill is received, Triangle Accounts Payable will enroll vendor in our “Auto-Pay” schedule by using either the bank or a corporate credit card.
Note on A237: John Ruppel: Our preferred phone vendor is Verizon. If Verizon cannot provide data service to the site/office, a suitable data vendor must be selected based on price, service and support offerings etc. Either Triangle IT or the liaison/site management can initiate the order request for data service at least 6 weeks prior to site startup date. The billing contact must be submitted as Triangle Corporate location along with 3 authorized contacts on the account. These contacts are (1) Accounts Payable staff members (2) Triangle Administration staff members and (3) Triangle Information Technology staff members. After the second bill is received, Triangle Accounts Payable will enroll vendor in our “Auto-Pay” schedule by using either the bank or a corporate credit card.
Note on A242: John Ruppel: Our preferred phone vendor is Verizon Wireless. If Verizon cannot provide data service to the site/office, a suitable wireless phone vendor must be selected based on price, service and support offerings etc. Either Triangle IT or the liaison/site management can initiate the order request for telephone service. The billing contact must be submitted as Triangle Corporate location along with 3 authorized contacts on the account. These contacts are (1) Accounts Payable staff members (2) Triangle Administration staff members and (3) Triangle Information Technology staff members. After the second bill is received, Triangle Accounts Payable will enroll vendor in our “Auto-Pay” schedule by using either the bank or a corporate credit card. Below is a high level overview of the flow of IT requirements for a new site/office setup:

## Corporate
|  | 2011-02-05 | 2011-02-12 | 2011-02-19 | 2011-02-26 | 2011-03-05 | 2011-03-12 | 2011-03-19 | 2011-03-26 | 2011-04-02 | 2011-04-09 | 2011-04-16 | 2011-04-30 | 2011-05-07 | 2011-05-14 | 2011-05-21 | 2011-05-28
ID | Task Name & Assignment(s) | 2011-02-05: WEEKS | Completed
|  | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | START | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Date | Comments
A | Corporate
JLL approval of Triangle Proposal
Finalized Contract between Customer (St. Louis Lambert Airport) and Triangle
Secure and deliver all contractually obligated insurance certificates to St. Louis Lambert Airport
Prepare a Contract Summary Guide for all Triangle management and supervision
Review PSA: Create categorical Summaries
Operational Requirements
Definitions
Pricing
Reports
Start up Deadlines
Equipment purchases
Supply (Chemicals & Paper) purchases
Procedures
Billing requirements
Locations with street addresses and customer designations
Customer conatct info by location
Assemble existing SOP's
Review all collected SOP's (with ?) for PSA compliance
Develop new SOP's requried to comply with PSA
Start-Up Team selection and assembly for preliminary review of entire Transition Plan. Present final Transition Plan to JLL for review and acceptance
Triangle Senior Management to meet with JLL management to review the contractual scope of work and insure compliance with same
Triangle Senior Management to attend JLLmeetings, as required
Triangle Senior Management and Account Manager to meet with Triangle dedicated supervisors and line staff to report on initial staff performance
Triangle senior management to meet with Triangle dedicated management to review the contractual scope of work and insure compliance with same
Triangle Management to review all policies and protocols to ensure complete compliance with same
Triangle Management to meet with MWBE representative to review all policies and protocols to ensure compliance with Triangle and JLL policies
Define and review monthly reporting formats with Triangle management
Define weekly reporting needs and format with Triangle management
Distribute summaries to start up team members, operations and Valley Stream
Establish audit process for measuring PSA compliance w/ corrective action
Plan audit dates
Assign responsibility for audits
Develop & Document Quality Plan-including inspection process
Develop & Document inspection forms (Local & Corporate Triangle, Customer)
Develop Customer Satisfaction Surveys
Review & Get Customer Approval on CS Surveys
Document Customer Satisfaction Process & Surveys (frequency, measurement, & feedback)
Document Compliment/Complaint Process
response, tracking, investigation, corrective action, Customer satisfaction resolution
Review mangement rules of authority
Review all (accounting, operations, safety, IT, etc) processes with local management (turnover)

## Finance Accounting
|  | 2011-02-05 | 2011-02-12 | 2011-02-19 | 2011-02-26 | 2011-03-05 | 2011-03-12 | 2011-03-19 | 2011-03-26 | 2011-04-02 | 2011-04-09 | 2011-04-16 | 2011-04-30 | 2011-05-07 | 2011-05-14 | 2011-05-21 | 2011-05-28
ID | Task Name & Assignment(s) | 2011-02-05: WEEKS | Completed
|  | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | START | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Date | Comments
B | Financial /Accounting
Obtain /review costing
Develop budget
Notify Valley Stream
Confirm codes, unit pricing etc
Set up in JDE
Confirm Local Tax Requirements
Coordinate/confirm with Valley Stream
License Company To Do Business In State
Sales Tax Certificate
State Tax Registration
Workers Compensation Policy Coverage & Reporting Forms
Liability Insurance Coverage & Reporting Forms
Unemployment Insurance Certificate
Certificate of Insurance for Customer
Performance Bond
Bank Accounts
Credit For Vendors
Check Cashing Arrangements
Establish communication between Valley Stream Staff and appropriate customer staff
Establish a St. Louis Lambert Airport account employee time clock payroll system
Establish internal financial reporting controls and account codes
Develop and Document key accounting processes
Accounts payable (includes requisition procedure)
Billing (includes how customer would like to see invoice)
Payroll - determine how to process

## Human Resources
|  | 2011-02-05 | 2011-02-12 | 2011-02-19 | 2011-02-26 | 2011-03-05 | 2011-03-12 | 2011-03-19 | 2011-03-26 | 2011-04-02 | 2011-04-09 | 2011-04-16 | 2011-04-30 | 2011-05-07 | 2011-05-14 | 2011-05-21 | 2011-05-28
ID | Task Name & Assignment(s) | 2011-02-05: WEEKS | Completed
|  | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | START | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Date | Comments
C | Human Resources
Review/Confirm staffing requirement and authorized position pay rates
Prepare/review Position Descriptions
Prepare recruiting plan
Place advertisements for required positions
Coordinate with Valley Stream notifying all BU's of open positions
Define candidate screening criteria (best candidate)
Document screening criteria for future replacement
Begin screening candidates
Prepare new hire packets
Schedule interviews
Review all interviewed candidates for consideration
Commence background checks and employment documentation of any St. Louis Lambert Airport proposed candidates that have been offered and accepted positions
Make final staffing recommendations
Select & Hire (final) qualified staff with Operations
Outline compensation, benefits and job description with selected candidates
Offer positions and obtain signed Letter of Understanding for each position
Obtain signed restrictive covenant from Management hires
Identify orientation and training requirements
Gov't mandated, Triangle values, equipment & chemical training
Prepare orientation and training materials
Prepare orientation and training schedule
Set up targeted job tax credits (WOTC) if applicable
Set up Employee personnel files
Designate shift assignments of all positions
Develop Organization chart with position names, phone numbers, & other pertinent info
Incorporate Organization Chart into Triangle's Master Organization chart
Forward all documentation requirements to Valley Stream
Ensure all training is completed per requirements
contact list of company expertise (including outside support)
Prepare & Document disaster recovery system
Prepare & Document absenteeism replacement or service interruption process
Prepare & Document employee retention program
Awards, commendation letters, core values, publicly acknowledge, communications length of service, attendance, safety, other KPI performance
Prepare & Document employee Perfromance Appraisal system
Post Federal and State labor law poster(s)

## CMMS
|  | 2011-02-05 | 2011-02-12 | 2011-02-19 | 2011-02-26 | 2011-03-05 | 2011-03-12 | 2011-03-19 | 2011-03-26 | 2011-04-02 | 2011-04-09 | 2011-04-16 | 2011-04-30 | 2011-05-07 | 2011-05-14 | 2011-05-21 | 2011-05-28
ID | Task Name & Assignment(s) | 2011-02-05: WEEKS | Completed
|  | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | START | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Date | Comments
D | CMMS
Review Cleaning Schedules for Tasking
Identify Tasking and Frequencies for Staffing
Define Tasking and Estimated Times for Scheduling of Staff
Verify Accuracy and Completeness of Tasking
Set up reports required per contract requirements
Determine/request input from customer re: their reporting requirements
Document Quality plan
Determine how work requests will be received from customer (phone, email, direct access call center, ect.)

## Equipment and Supplies
|  | 2011-02-05 | 2011-02-12 | 2011-02-19 | 2011-02-26 | 2011-03-05 | 2011-03-12 | 2011-03-19 | 2011-03-26 | 2011-04-02 | 2011-04-09 | 2011-04-16 | 2011-04-30 | 2011-05-07 | 2011-05-14 | 2011-05-21 | 2011-05-28
ID | Task Name & Assignment(s) | 2011-02-05: WEEKS | Completed
|  | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | START | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Date | Comments
E | Equipment & Supplies
Complete inventory of Airport Purchased Equipment and place order if needed for new equipment
Disposables initial order processed
Take delivery of all supplies and conduct inventory check
Field test all equipment
Validate supply inventory levels

## Safety
|  | 2011-02-05 | 2011-02-12 | 2011-02-19 | 2011-02-26 | 2011-03-05 | 2011-03-12 | 2011-03-19 | 2011-03-26 | 2011-04-02 | 2011-04-09 | 2011-04-16 | 2011-04-30 | 2011-05-07 | 2011-05-14 | 2011-05-21 | 2011-05-28
ID | Task Name & Assignment(s) | 2011-02-05: WEEKS | Completed
|  | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | START | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Date | Comments
F | Safety
Identify Safety officer forwarding contact information to the Director of Safety
Complete Certification of Hazard Analysis. Signed copy retained in the site safety records. Copy forwarded to the Director of Safety.
Identify Personal Protective Equipment cited on the Certification of Hazard Analysis
Conduct and document training for use and care of personal protective equipment for each employee
Set up Occupational Injury, Auto Loss and General Liability reports
Require all personnel to sign off acknowledging accident reporting procedure with copies sent to Director of Safety
Print Corporate Safety Manual printed and make available to all employees
Complete/document training session for all employees concerning contents and location of Corporate Safety manual
Develop site specific safety handbook
Conduct/document training conducted for site specific safety manual awareness
Confirm Job Hazard Analysis procedure and form are on site
Complete New Hire Orientation form for each employee
Employee training document template on site
Set up Monthly Safety Training attendance record template
Set up Annual Safety Training Topic template
Create MSDS book in accordance with corporate policy
Training for MSDS and chemical use has been completed and documented for all employees
Chemical storage area(s) organized in accordance with corporate policy
Confirm flammable storage lockers on site for storage of ALL flammable materials
Secure training areas
Conduct classroom training of janitorial staff
Conduct on-site training of ramp and cabin grooming staff
Identify occupational health facility, which will provide new hire physicals, drug and alcohol screening and work related injury care.
Verify first aid kit is on site and sufficient for number of employees in the work center, install if needed.
Post any safety poster(s)
Verify that offices and work areas have proper signage, install if needed (first aid kit, eye wash station, fire extinguisher, hearing protection areas, stretcher, etc)
Refresher safety and security orientation and training with Triangle and MWBE staff
Security and safety orientation of St. Louis Lambert Airport protocols
Obtain copies of St. Louis Lambert Airport protocols and establish training formats and schedule
Modify Triangle training materials according to St. Louis Lambert Airport standards
Determine safety and security policies and regulations in accordance with St. Louis Lambert Airport security policies and procedures

## Administrative
|  | 2011-02-05 | 2011-02-12 | 2011-02-19 | 2011-02-26 | 2011-03-05 | 2011-03-12 | 2011-03-19 | 2011-03-26 | 2011-04-02 | 2011-04-09 | 2011-04-16 | 2011-04-30 | 2011-05-07 | 2011-05-14 | 2011-05-21 | 2011-05-28
ID | Task Name & Assignment(s) | 2011-02-05: WEEKS | Completed
|  | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | START | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Date | Comments
G | Administrative
Identify/secure office space
Identify/secure locker room space
Identify/secure storage space
Identify/secure office furniture and basic office set up supply requirement
Identify/secure communication requiremnts w/ IT department
Computer, fax, electronic time keeping, Phone lines or cable, cell phones
Secure Triangle and STL Lambert Authority ID Badges for all employees
Requisition/purchase authorized office equipment
Order corporate signage for door, if required
Confirm all employment posters are in place
Order business cards for authorized personnel
Order stationary, company forms, and stationary supplies
Identify required keys and or lock codes for space
Coordinate start up with VP of HR, Director of Safety, CFO, and COO to confirm that all items needed for account setup and required documentation have been received.
Submit Material Safety Data Sheets (MSDS) on planned chemicals to St. Louis Lambert Airport for review and approval, as required
Define any customer service, procedural and QC forms required by St. Louis Lambert Airport
Create above forms, as required, and review for accuracy with St. Louis Lambert Airport
Transition and start-up meetings with local St. Louis Lambert Airport management
Conduct introductory meetings with St. Louis Lambert Airport local operations department heads
Core Values - posted in office

## Operations
|  | 2011-02-05 | 2011-02-12 | 2011-02-19 | 2011-02-26 | 2011-03-05 | 2011-03-12 | 2011-03-19 | 2011-03-26 | 2011-04-02 | 2011-04-09 | 2011-04-16 | 2011-04-30 | 2011-05-07 | 2011-05-14 | 2011-05-21 | 2011-05-28
ID | Task Name & Assignment(s) | 2011-02-05: WEEKS | Completed
|  | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | START | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Date | Comments
H | Operations
Obtain Purchase Order or copy of signed Contract
Review contract requirements
Evaluate Start-Up Team Requirements
Select Start-Up Team Individuals
Assign Category Coordinators
Select Start-Up Team Leaders
Define Start-Up Team Lines of Authority & Responsibility
Define and communicate expense guidelines to start up team
Set Up Pre-Planning Meeting with Start-Up Team
Prepare list of key requirements for distribution to all start up staff
Set Up staffing plan including start/stop times
Set up emergency contact procedures including how to contact all staff
Establish planned lines of communications with Customer
Requisition, purchase, obtain required materials and equipment
Capital equipment
Supplies
Uniforms
Conduct uniform fittings
Order Triangle uniforms
Distribute Triangle uniforms
decide how to wash mop heads and rags
Forward Insurance Certificate to Customer
WorkLoad Facilty to determine:
Manhours, cleaning tasks & asignments, equipment requirements
Document work loading assignments w/ time allocation, proper chemicals & equipment)
Develop & Document process to handle out of scope work
(special requests with time of completion, emergency, disaster)
Finalize Job Costing Budget (Cost Analysis Sheet)
Set up Budget Control Process (labor hours & $, supplies) w/ corrective action if over budget
Get Approved vendor list of suppliers/equipment manufacturers and subs
Finalize/signAgreement with Subcontractors - provide insurance, non compete, agrees to follow all Triangle procedures at site
Get W9 Forms from Subcontractors
Get Insurance Certificates from Subcontractors
Meet with Customer's Security representative to review security requirements, including the following:
Sign In Requirements
Alarm Systems
Key or Access Card Systems
Safety and Emergency Procedures
Trash Handling Requirements
Areas to be Cleaned with Tenant or Security Present
Call in 3 approved equipment manufactures to recommend best equipment usage
Have each equipment manufacturer provide benefits over competitor equipment
Get equipment spec, warranties, training requirements, equipment maintenance requirements
Call in 3 approved distributors to recommend best chemical usage
Have each distributor provide benefits over competitor chemicals
Get chemical spec, warranties, training requirements, MSDS sheets on all cemicals
Develop and document an approved vendor, equipment, & chemical plan
Develop and document an inventory control plan
Develop and implement an equipment maintenance PM program to match manufacturer's spec
Conduct any skill training required (equipment & chemical)

## IT
|  | 2011-02-05 | 2011-02-12 | 2011-02-19 | 2011-02-26 | 2011-03-05 | 2011-03-12 | 2011-03-19 | 2011-03-26 | 2011-04-02 | 2011-04-09 | 2011-04-16 | 2011-04-30 | 2011-05-07 | 2011-05-14 | 2011-05-21 | 2011-05-28
ID | Task Name & Assignment(s) | 2011-02-05: WEEKS | Completed
|  | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | START | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Date | Comments
I | Information Technology
Hardware requirements
Identify office equipment requirements inclduing telephone, fax
machine, internet, copier, computer's, answering machine, etc
Submit hardware required to Triangle IT Dept
Hardware ordered from vendors and shipped to support company for configuration
Hardware shipped to new site
Software requirements
Confirm standard office package (utilities, Adobe Reader, Office)
Identify additional software or needs (JDE, EAM )
Phone requirements
Order necessary lines and equipment for new site
Data requirements
Order necessary lines and equipment for new site
Firewall hardware shipped to support company for configuration
Office network wiring installed and additional hardware ordered
Network tested and documented
Mobile phone requirements
Preferred vendor is selected
Hardware types are decided
Hardware shipped to new office
Secure all St. Louis Lambert Airport e-mail addresses and telephone contacts, distribute to appropriate Triangle staff
Review and conform to company polices
Note on B7: John Ruppel: Triangle IT needs to know how many computers, monitors, printers etc the office requires. Once Triangle IT has a complete list, the equipment will be ordered and shipped to Triangle IT Support Group for configuration. It will then be shipped to the designated address. Setup and configuration will be coordinated by Triangle IT Support Group along with site liaison or site management. All future purchases will be coordinated with IT as well.
Note on B13: John Ruppel: All Triangle computers have the XP operating system installed as a standard. They are also pre configured with MS Office 2003 and Adobe Acrobat Reader. If the office or site requires any additional software, these will be purchased and installed by Triangle IT as part of the hardware setup.
Note on B16: John Ruppel: Our preferred phone vendor is Verizon. Either Triangle IT or the liaison/site management can initiate the order request for telephone service at least 6 weeks prior to site startup date. The billing contact must be submitted as Triangle Corporate location along with 3 authorized contacts on the account. These contacts are (1) Accounts Payable staff members (2) Triangle Administration staff members and (3) Triangle Information Technology staff members. After the second bill is received, Triangle Accounts Payable will enroll vendor in our “Auto-Pay” schedule by using either the bank or a corporate credit card.
Note on B18: John Ruppel: Our preferred phone vendor is Verizon. If Verizon cannot provide data service to the site/office, a suitable data vendor must be selected based on price, service and support offerings etc. Either Triangle IT or the liaison/site management can initiate the order request for data service at least 6 weeks prior to site startup date. The billing contact must be submitted as Triangle Corporate location along with 3 authorized contacts on the account. These contacts are (1) Accounts Payable staff members (2) Triangle Administration staff members and (3) Triangle Information Technology staff members. After the second bill is received, Triangle Accounts Payable will enroll vendor in our “Auto-Pay” schedule by using either the bank or a corporate credit card.
Note on B23: John Ruppel: Our preferred phone vendor is Verizon Wireless. If Verizon cannot provide data service to the site/office, a suitable wireless phone vendor must be selected based on price, service and support offerings etc. Either Triangle IT or the liaison/site management can initiate the order request for telephone service. The billing contact must be submitted as Triangle Corporate location along with 3 authorized contacts on the account. These contacts are (1) Accounts Payable staff members (2) Triangle Administration staff members and (3) Triangle Information Technology staff members. After the second bill is received, Triangle Accounts Payable will enroll vendor in our “Auto-Pay” schedule by using either the bank or a corporate credit card. Below is a high level overview of the flow of IT requirements for a new site/office setup: